## Sheet1
Check 25-09-2026 | 4.1 Source 1 — Trustee Review Portal (2026-09-07)
| Id | What Emily asked for | Surface | Resolution | Reserve | Proposed solution | Size | Depends on / conflicts with | Status after deployment
Done | EF-01 | Region shown in the grant portal the grant admin uses | Grant admin app | in-baseline | A4 — 4.5 | Region is already captured and readable by the grant admin as Location Area on the Applicant record. Surface it on the Application record, read-only, where casework happens | S | Bundle with EF-38 (Δ4 EF-18 dropped — self-serve). Δ4 The re-check is answered: the grant admin's column holds county (EF-40), and trustees see no location at all (EF-02). One column, one audience | This item changed because of the item about no location at all and the discussion about a change order. For which I saw an changer order I approved, but no new plan to build it.
Partly done, see comments about the trustee role | EF-02 Δ | Region must not be visible to trustees | Column security | in-baseline | A6 — 6.8 | Δ4 Settled 2026-09-17: trustees see no location at all. A permissions change, not a UI change — rev_locationarea is unsecured, so trustees can read it from any surface, not only the one that displays it. Add it to REV_TrusteeRestricted, drop the location column from ApplicationsTable, and drop the region filter in ApplicationFilters with it, or the filter keeps offering the values through its option list | S | Δ4 A live disclosure again, and now definite — revision 4 briefly tabled a reading where trustees saw county; they do not. Reduces a contracted deliverable: WBS 6.2 specifies the list screen as "applications with score, region, dates, status" and it ships with no location column — pm-agent should record that against 6.2. rev_agerange is unsecured on the same footing, still unmentioned by Emily. Δ4 No longer sequenced behind EF-40 — one column, different audiences | Region column is not visible anymore in the Trustee Portal. Location Area in the Securiy role is still set to allowed for Read, Create and Update. Noticed something else, Trustee Restricted security profile has lots of items on allowed, where they should be the other way around.
There is a city derived column and the wordpress to dataverse flow has new actions. Can't test it yet because of dependency web builder | EF-03 Δ4 | A city identifier derived from the postcode, because the typed city field is unreliable | Intake flow + schema | change-order-candidate | — | No city derivation exists. The city shown today is rev_towncity, the applicant's own typed answer — exactly the unreliable value Emily describes. Region is derived from postcode at intake via the PostcodeRegionMap setting, so the pattern exists, but that map holds regions, not settlements. Δ4 The file has arrived and carries a Main Postal Town / City column keyed on postcode district — the lookup is now specifiable | M (was L) | Δ4 Licence blocker effectively gone — the file is neither PAF nor ONSPD (§2h). Replaced by two quality limits: no alphanumeric London codes, and a County column that is not a county in 30% of rows | We settled on a new column on applicant. But no new column has been created.
Not done yet | EF-04 Δ4 | Mirror the current Trustee Pack's setup and wording | Trustee portal | in-baseline | A6 — 6.8 | Re-label and re-order the detail screen to follow the pack the board already knows. Δ4 The pack has arrived and its order is now specified, not inferred: Summary → Application Details → About Applicant → Current Circumstances → Financial Eligibility, with the score in the Summary at the top and the question detail well below it | M | Δ4 Dependency DELIVERED — docs/Import/3. Round 4 - Individual Applications.pdf. This item is ready to build | The order of items in the Trustee Portal, on the individual application screen are not the same as the example in the file. The order of items need to be verbatim as the PDF. The first two pages of the file are for 1 application. And the desription of this item is correct.
Done | EF-05 Δ | Notes compulsory for a rejection | Trustee portal | in-baseline | A6 — 6.8 | Notes are optional today on all three verdicts — VerdictForm labels the field Notes (optional). Δ Require notes on Reject and Defer, using the same inline validation the verdict radio already uses; leave Approve optional | S | Δ Open question closed. Revision 2 asked whether Defer should also require a note; the walkthrough answers yes | These items are processed correctly, both an defer and reject now need a note.
| EF-06 | What is included in the anonymised narrative section? | Trustee portal | answer-only | — | Nothing today, by design. The panel binds the redacted narrative column and nothing else. Narrative scrubbing (Automation #5) is deferred under exception EX-003, so the panel stays withheld until that automation is built | — | The answer doubles as a warning: EX-003 clears only when Automation #5 lands and DPO sign-off arrives, before any live trustee demo
Not done yet | EF-07 Δ4 | Move the full wellbeing answers lower down, show the actual questions and answers, keep only the score out of 60 at the top | Trustee portal + scoring flow | in-baseline | A6 — 6.8 and A2 — 2.7 | Two halves: the flow writes the breakdown with question text and the answer's label instead of "Wellbeing answer 3: response 2 = 4 points" (A2); the portal shows the score alone at the top and the expanded breakdown lower down (A6). Δ4 The pack confirms the exact target format — "I've been feeling optimistic about the future · None of the time". Emily's EF-24 example was quoting her own pack | M | Same underlying change as EF-24. Δ Now conflicts with the audit-column ask — resolved by the split in §2c and EF-44. Build EF-44 first; EF-07 and EF-24 then write to the trustee-facing half only. Δ4 Note the two answer scales — the seven two-week statements use None of the time…, the three last-year statements use Strongly disagree… (gap M-02, now evidenced) | Wellbeign answers are not moved down in the trustee portal. The order of items are still not correct and the wellbeing answers don’t have the actual questions
Done last round | EF-08 | Holiday Details → Application Details | Trustee portal | in-baseline | A6 — 6.8 | Rename the panel. The live form's section 13 is already called Application Details | S | Settled without further input, per the §1 principle | This is delivered.
Not done yet. | EF-09 Δ4 | Preferred Dates → Start and End Date | Trustee portal | in-baseline | A6 — 6.8 | Rename and split the single row into two | S | Δ4 Still blocked, and the reading is now settled (§2f). The columns and the intake bindings exist — our half is built — but the live form asks one free-text Provisional date (field 75, V-04), so nothing fills them. The two dates in the packs are Emily's own manual entry. Once field 75 becomes two date pickers this is a portal rename and nothing more | This has not been delivered. It still mentions preferred dates in the application detail section.
Done last round | EF-10 Δ | Helper, referee and contact details should not be in the Trustee Portal | Trustee portal + column security | in-baseline | A6 — 6.8 | Two halves, one of them not cosmetic. The helper, referee and emergency-contact names, emails and phone numbers are already behind REV_TrusteeRestricted and render as withheld placeholders — the portal's generated restricted-field catalogue groups all eight under "Helper, referee and emergency contact", which is exactly the panel Emily names. Removing it is presentation. Helper Organisation and Helper Relationship are not in the profile and are readable by trustees today. Secure those two, then remove the panel | S | A live disclosure, not a preference. Δ Confirmed at the walkthrough, which named emergency contact explicitly alongside helper and referee | This is delivered and not visible anymore on the application detail page.
Not done yet | EF-11 | Remove Days the round has been open — not a representative figure | Landing screen | in-baseline | wbs:6.9 — CO-001 | Remove the tile from RoundStatistics | S | Δ Still open — the walkthrough did not settle it. Applications per day is computed from the same day count Emily calls unrepresentative, so removing one and keeping the other is half a fix. Carry the question into the return email | This can't be checked, because the round statistics workflow can't be turned on. When I open that workflow, it can't be saved because of an error with the definition. The action set trailing 2 says variable not initialized. But I can't find that action in the flow.
Not done yet | EF-12 Δ4 | Add wording for the wellbeing question 8, 9 and 10 statistics, and the circumstance score | Landing screen | split — in-baseline + change-order-candidate | wbs:6.9 / CO-001-A3 | Wording half — in-baseline: label the three last-year charts with their full question text, taken from the pack. Circumstance-score half — new: there is no circumstance-score distribution, and CO-001's priced chart list does not include one | S / S | Δ4 Closed by document, not inference. The pack groups the questions under literal headings "In the last 2 weeks…" (seven) and "In the last year…" (three). 8, 9 and 10 are the last-year three. Drop the confirming question from the return email | Can't be checked because of the round statistics workflow that is not running now.
4.2 Source 2 — Grant administrator application (2026-09-08)
| Id | What Emily asked for | Surface | Resolution | Reserve | Proposed solution | Size | Depends on / conflicts with
Done | EF-13 | A simple end-to-end process flow of how the process works | Documentation | in-baseline | A0 — 0.6 / 0.8 (no reserve) | A process flow already exists — docs/Import/Revitalise-Process-Flow-v0.1.html, a July 2026 draft. Sendable today but stale: it says the application "lands in SharePoint", which is not what was built. Refresh to as-built and re-issue | S | One of the items landing on A0, which has no feedback row | Was already present.
| EF-14 | Some sections show a locked symbol — will the grant admin receive all access? | Access model | answer-only | — | Yes, with one deliberate exception. The padlock marks a column-secured field; the grant admin role is a member of the profile that releases them. The exception is bank and payment data, behind a second profile the grant admin is deliberately excluded from | — | Worth stating as a control she benefits from, not a limitation
| EF-15 | Auto-reject cases added as a category under Casework | Grant admin app | answer-only | — | Already built — Auto-rejected Applications sits under Casework with its own saved view | — | Confirm this is what she meant
Done last round | EF-16 Δ4 | Auto-pass cases added as a category under Casework, to check the free-text answers are sufficient | Grant admin app | in-baseline | A2 — 2.7 | Add an Auto-pass Applications saved view and a Casework sub-area beside the existing four (Applications, Borderline — Awaiting Review, Under Review — Incomplete Scoring, Auto-rejected Applications) | S | Δ4 The bucket is 81% of the round, not an exception queue. At the provisional threshold, Round 4 splits 1 auto-reject / 11 borderline / 51 auto-pass (§2j). A flat saved view will not organise 51 applications needing a qualitative read. Sequence after EF-46 and size against the real number | This is delivered.
| EF-17 Δ5 | A section at the end containing the full application | Grant admin app Trustee Portal | Δ5 out-of-scope for this application | — | Δ5 Settled 2026-09-18 (§2l): the transcription places this ask in the Trustee Portal, not the grant admin app. Nothing is built here. If a Trustee Portal equivalent is wanted it is a new item requiring its own triage — the "section or tab" and "form ordering" questions below no longer need settling for this codebase | — | Δ4 (superseded by Δ5) Two things to settle before this is built or sized. Section or tab? She asked for a section at the end; the plan turned it into a tab, which is a structural choice that now sits beside EF-47's Casework tab and should be made deliberately. And keep or drop the form ordering? The rationale is real but constructed — EF-22 and EF-37 both ask for the form's own structure and wording, so form order is consistent with them — it is simply not something she asked for. Cheap to keep, so say it is ours. Overlaps EF-37 — both need the form's question text
| EF-18 Δ4 | Include personal details in the application — name, address, email | Grant admin app | Δ4 answer-only — no build | — | Δ4 Dropped 2026-09-17: Emily can do this herself. What she wants is related columns on the application views, which a user adds through Add Columns > Related > Applicant without a maker. Revision 4 proposed surfacing the identity fields on the Application form instead — that would have been ours to build, and it is not what she needs | — | Δ4 Dropping it keeps a design intent the build would have traded away. The Application record deliberately shows a pseudonymised reference; putting names on the form would have been safe only because column security carries it, never the layout. Not building it leaves the pseudonymisation intact and the names one view away. Unbundled from EF-01 and EF-38, which remain form changes
| EF-19 | Quality Monitoring — where are these recorded? | Grant admin app | answer-only | — | The form's final section is called Equality Monitoring — gender and ethnic group. Both are on the Applicant record, both column-secured, both readable by the grant admin, and neither reaches scoring or eligibility | — | Confirm the reading with her
| EF-20 Δ | Intake Review Note — assuming I will have access to all of these? | Grant admin app | answer-only | — | Yes — and Δ the walkthrough showed the real question is what it contains, not who can read it. It is written by the intake flow when a Choice answer arriving from the form matches no configured option: the field, the raw value, and that no match was found. Empty when every answer mapped | — | Δ Closes a Xander action item outright. It is a data-quality log, not a caseworker's note
Done | EF-21 Δ4 | Selectable categories in the Intake Review Note as well as free text Yes/no review checkboxes plus one free-text note | Grant admin app | in-baseline | A4 — 4.5 | Δ Superseded — see §2b. A new per-application review section. Do not attach these to rev_intakereviewnote, which is machine-written. Δ4 The items have arrived and there are eight, not five: Location · Date · Amount · Exceptional Circumstance · Disability Information · Care Information · Group · Age. They land on the new Casework tab (EF-47) | S → M | Δ4 Dependency DELIVERED in the 16 September mail body. Δ4 Settled 2026-09-17: build all eight — tell Emily, she asked. Nine new columns on rev_application, all with no default value so "not yet checked" stays distinguishable from "checked, no" (§2e). Δ4 What it is, per the reviewer 2026-09-17: Emily's own mental check made visible, run before an application goes to the trustees — a permanent workflow control, not a workaround (§2e). No item elsewhere in this plan retires a box. Place it immediately before rev_eligibleforround on the Casework tab — check, then release | These items are delivered and on the caseworker tab
Done | EF-22 Δ4 | Split the scoring into three sections: Life satisfaction / In the last 2 weeks… / In the last year… | Grant admin app | in-baseline | A2 — 2.7 | This is the form's own structure — one 0–10 scale, seven two-week statements on a 5-point scale, three last-year statements on a 6-point scale. Δ4 And it is the trustee pack's structure too, under those literal headings, so the same split serves both surfaces | S | Underlines a real data issue: the three last-year questions use a different answer scale from the seven two-week questions (gap M-02). Δ4 Now evidenced — None of the time… versus Strongly disagree… in the live packs | These items are delivered and on the general tab of the application form
| EF-23 Δ4 | What does "No Rounding was Applied" mean? | Scoring flow | answer-only + in-baseline | A2 — 2.7 (for the removal) | Δ4 Remove the whole rounding passage, not just the one message — no rounding takes place. Confirmed by the reviewer 2026-09-17 and verified in the seeded settings: LikertPointMap gives Not sure (key 6) 0 points, "CHANGED FROM 0.5 on 2026-08-20 and confirmed with Emily… the map now holds no fractional value, so the half-point rounding can never fire". The breakdown writes Exact total before rounding and a rounding sentence; both go | S | Δ4 Two things the removal should not leave behind. Round_the_circumstance_score is now dead code — half-up via formatNumber with a +0.25 offset, fixed under D-015 when halves still existed. Remove it, or keep it as a deliberate guard and say so; do not leave it unexplained. And the flow's own descriptions are stale in three places, still asserting "'Not sure' is worth 0.5 points (map key 6)" — they contradict the map that actually runs and nearly had this item reversed (IMP-0747). Fix them in the same change | This is delivered and not present anymore.
Done | EF-24 | Break the score breakdown down by question — "I've been feeling optimistic about the future: response 1 = 5 points" | Scoring flow | in-baseline | A2 — 2.7 | Emily wrote the target format herself. Write the question text and the answer's label instead of a question number and a response number | S | Same change as EF-07. Δ Sequenced after EF-44 | This item is not processed in the power automate flow. There is a split between the score and the audit field with separate compose steps. But the labels of the questions are still not corrected to the actual questions
Done | EF-25 Δ4 | Knockout → Low band → Threshold → Threshold score, across the entire app | Scoring flow + Settings + docs | in-baseline | A2 — 2.7 | Δ Superseded — see §2b. Change the word wherever a person sees it: score-breakdown text, Setting display label, sitemap, role definition, test fixtures, and docs/training/casework-handbook.html. Δ4 The word is settled: Threshold score, agreed by the reviewer 2026-09-17 | S → M | Change the label, never the Setting row's name. The row is KnockoutThreshold and the flow looks it up by rev_name in all three environments. Δ4 Agreed, and no longer a question — the reviewer confirmed 2026-09-17 that Threshold score is already agreed, so it left §5a's question list. Build it | The audit field now uses the term Threshold score.
| EF-26 | What does the "Override" section show? | Grant admin app | answer-only | — | It records a manual override of the automated outcome by the process owner: whether it was overridden, by whom, when, the reason, and the decision date — rev_statusoverridden, rev_overriddenby, rev_overriddenon, rev_overridereason, rev_decisiondate | — | Δ Already answered by this plan before the walkthrough re-asked it. Pair with EF-34, which increases how often an override will be needed
Done | EF-27 Δ4 | An action completed record for safeguarding incidents | Grant admin app | in-baseline | A0 — 0.4 (no reserve) | Δ4 Now specified to the column. An Action Completed checkbox beside rev_safeguardingflag and rev_safeguardingnotes, with a dedicated safeguarding completion date — its own column, not a general one reused (reviewer, 2026-09-17). Specifically not rev_decisiondate, which belongs to the Override section and means the decision on the application, nor rev_overriddenon. Name it for safeguarding, e.g. rev_safeguardingactioncompletedon. Set by the platform on tick and read-only on the form, so it cannot be backdated | S | Δ4 Three new columns, and the security basis is verified rather than assumed. rev_safeguardingflag and rev_safeguardingnotes are both IsSecured=1, "Admin + Service only, never trustee-visible — a staff escalation matter"; the date and the owner column take the same treatment. Still recommend capturing who ticked it — a safeguarding action with a date but no owner is weak evidence. Commercial note: this is three columns on an item whose reserve is A0, which carries none (§6, the reserve model holds, with the same hole). Lands on the Casework tab (EF-47) | The field is there, but when I select yes the date field (safeguarding completed on) and the safeguarding completed by fields are not populated. This is missing from the solution
Done | EF-28 Δ | Means-tested benefits moved to the front | Grant admin app | in-baseline | A4 — 4.5 | Δ Now specified to the exact order: Received means-tested benefits → Benefits provider → Income band → Income flag (rev_receivesbenefits, rev_benefitprovider, rev_incomeband, rev_incomeflag — all four exist). Our app currently puts Income Band first | S | Raises gap M-04: if the four dependent questions are ever suppressed, an absent income band must be read as qualifies on benefit status, not as missing data | This is delivered and present on the eligibility and finance tab
| EF-28b Δ4 | "If they select yes they are not asked about income, employment status or savings" | Upstream WordPress form | Δ4 answer-only — already built | A1 — 1.2 / 1.4 (spec side) | Δ4 CONTRADICTED, then settled. This plan said the form does not suppress. Round 4 shows 57 of 57 blank on a Yes, 6 of 6 populated on a No, and the reviewer confirmed it against the form on 2026-09-17: when benefits are selected, income does not have to be filled in. Already built — not Alex's, nothing to re-test | S (ours) | Δ4 Resolution changes to answer-only. The consequence is EF-28's: gap M-04 now has a designed fix — a fourth rev_incomeflag option, Qualifies on means-tested benefits, evaluated before the income test (§2i). Without it 90% of applications carry "Not stated — cannot assess"
Partly done.. Income band option set not adjusted to new income band options | EF-29 Δ4 | Income bands set as per the form | Schema + spec | in-baseline | A1 — 1.4 (decision) · A2 — 2.7 (implementation) | Δ4 SETTLED — three sources now agree. Emily's 16 September mail body lists four bands — Under £15,000 · £15,000–£25,000 · £25,000–£35,000 · Over £35,000 — duplicated on the attachment's Income Values sheet and matching the 2026-09-11 capture exactly. IncomeBandUpperBoundMap's five bands on £10K boundaries are the outlier and are wrong | S/M | Δ4 Dependency DELIVERED. NFR-019 holds for the bands: the map changes, the scoring flow does not. Δ4 Trim the option set in the same pass: drop Prefer not to say — the form never offered it, the committed sets were placeholders (M-07, OPEN-20), and with only demo data in DEV and ACC the trim is safe now and unsafe once a real application is scored (§2h). No migration question: there is nothing real to migrate. Cosmetic: both of Emily's copies list Over £35,000 third — take the set as authoritative and the order as a slip | This is no delivered. The seeded settings are still the old 5 band income band value. Also the income band choice field on the application table from, still shows the old values.
| EF-30 | Employment status as a dropdown as per form | Schema | answer-only | — | Settled, and nothing needs to change. The live form's five options are exactly what rev_employmentstatus holds, and EmploymentStatusLabelMap maps them | — | Verified against the form capture; the schema was right
Not done | EF-31 Δ4 | Automatic flag when the amount requested exceeds £500 (holidays/respite) or £100 (day trips/activities) and no exceptional funding request was made | Δ Upstream form + scoring flow | Δ split — external-dependency + in-baseline | A1 (form block) · A2 — 2.7 (existing corpus) | Δ Reframed — see §2b. Δ4 Build both — settled 2026-09-17. Δ4 And now specified, because “the A2 flag” named no column and no surface. Only two flag columns exist, rev_incomeflag and rev_safeguardingflag, so there is nothing today to record it in. Add a two-option column on rev_application, e.g. rev_exceptionalfundingmissing, with no default value so not yet scored stays distinct from scored and fine. Put the thresholds in a setting, not a literal — seeded in all three environment files like KnockoutThreshold. Δ4 And make it a map, not a scalar: £100 was confirmed still live on 2026-09-17, so the check is break-type dependent and a single ExceptionalFundingThreshold row cannot express it. Seed a ExceptionalFundingThresholdMap keyed by rev_breaktype option — the same shape as AgeBandMap and PostcodeRegionMap, which the flows already read — so Other and any later break type are a row rather than a code change. Set it in the scoring flow's existing pass, beside status and rev_incomeflag: rev_amountrequested over the threshold and rev_exceptionalfundingrequested not true | M | Δ4 Shown to the admin in the two places this solution already uses for triage: a saved view plus a Casework sub-area, the same shape as Borderline — Awaiting Review, and on the form on the Casework tab beside rev_incomeflag (EF-47) — both are machine-derived triage flags. Not a rev_applicationstatus value: status is the assessment stage, and overloading it would conflate where is this in the process with this needs a look, fighting EF-16's bucket. Δ4 Scale, measured: the flag catches nothing in the corpus we hold. 13 of 63 Round 4 applications exceed £500 and all 13 carry an exceptional amount; Round 5's groups are at £500 or below. So the A2 half is a safety net, not remediation — which lowers its urgency without changing the decision to build it. Δ4 Both thresholds are settled: £100 still applies (2026-09-17), so EF-32 survives and becomes a precondition — the rule cannot run until Other's treatment is stated. Δ4 The £100 half is now measured too, and it behaves the same way: 5 of 63 are day trips or activities, one exceeds £100 and it carries an exceptional amount, so the flag still catches nothing. Δ4 But the boundary is the real specification risk (§2j). 35 of 63 request exactly £500 and 4 exactly £100 — the cap is the modal value, not a ceiling people approach — so > flags 0 and >= flags 37 of 63. Pin exceeds, strictly in the spec and in a test fixture; the walkthrough's word was exceeds and the collision is what makes leaving it implicit dangerous | This is not delivered. I don't see a flag that comes up when an item has more that 500 GBP requested and no exceptional funding requested.
| EF-32 Δ5 | Unsure how "other" should be treated | Business rule | Δ5 closed — confirmed, no build | — | Confirmed 2026-09-18: Other takes no automatic threshold and is flagged for manual review, exactly as proposed | — | Δ May be moot. It exists only because two thresholds needed a break-type test. A single >£500 rule does not Δ4 Not moot — promoted to a precondition of EF-31. £100 was confirmed still live 2026-09-17, so the check is break-type dependent and Other is the break type that answers neither threshold. Δ4 And it now has numbers rather than a preference (§2j): 4 of 63 Round 4 applications are Other; giving them £100 flags 2, giving them £500 flags 0, giving them nothing flags 0. Δ5 Confirmed as sent — EF-31's A2 half is now unblocked on this precondition
Done | EF-33 Δ4 | Costs and Funding moved into the Break Details section | Grant admin app | in-baseline | A4 — 4.5 | Δ4 It is hers, verbatim, and easy to miss. Source 2, 2026-09-08, numbered item 5: “Costs and Funding – / To include in ‘Break Details’ section”. Two lines, no discussion, and the walkthrough never returned to it — which is why it reads as coming from nowhere. Ours: that it currently sits on the Eligibility & Finance tab (verified in the form) and that “include in” means move rather than also show | S | Δ4 Worth one word of confirmation: move or duplicate? Include can mean either, and the plan assumed move. Moving is the coherent reading — items 1–4 of that same list are all eligibility and finance fields she wants kept together, and the costs describe the break rather than the applicant's means. Presentation only: no automation reads a field's tab. Note the neighbour: rev_amountrequested travels with the section, and it is what EF-31's new flag tests — the flag stays on the Casework tab, the amounts move, which is EF-47's dividing line working as intended | This is delivered and present on the Break Details tab.
Done | EF-34 Δ | A No to previous funding more than 12 months ago should be auto-rejected | Scoring flow | in-baseline | A2 — 2.7 | Δ Now stated as an explicit compound condition: received funding before is Yes and more than 12 months ago is No → auto-reject. Both columns exist (rev_receivedfundingbefore, rev_morethan12monthsago) and no automation reads either today | S/M | Conflicts with an open compliance decision. Whether automatic rejection may stand without human review is open for the DPO under the Data (Use and Access) Act 2025 (rule BR-S10). Δ The compound form makes this sharper, not safer — it is a second fully automatic rejection path. Recommend routing the outcome to the process owner rather than closing the application until the DPO decides | This is not delivered or not working. The conflict is not applicable because all items get checked by a human, regardless of their automatic scoring.
Done | EF-35 Δ4 | A new form question: carers confirm the person they support is over 18 | Upstream WordPress form | Δ4 in-baseline — our half is no longer blocked | A1 — 1.2 / 1.4 · A4 — 4.2 | Confirmed genuinely absent — the live form has “I confirm I am 18 years of age or over” for the applicant and no equivalent for the person supported. Δ4 Alex is adding it, so expand the data model now rather than waiting (reviewer, 2026-09-17). Mirror the existing pair exactly: rev_ageconfirmationconsent (bit) and rev_ageconfirmationconsentdate (datetime) become rev_supportrecipientageconfirmation and its date. Add the trigger keys to REVIntakeWordPressToDataverse and bind them in the same change, so the data flows the day Alex ships with nothing further from us | S (ours) | Δ4 No default value, or every application captured before Alex's change reads as confirmed not over 18 rather than never asked — the whole corpus, on a safeguarding-adjacent field. And record the gap deliberately: binding a key the form does not yet send is precisely M-10, “accepted by the intake, never sent by the live form”, which is a list of defects. Add the row with a date and Alex as owner, or the next reader flags it as one — exactly as this plan did with the break dates (IMP-0744). Δ4 Unblocks EF-36's second half, which can now be built against the column ahead of the form | This new column is not present on the form of the application table.
Done | EF-36 Δ4 | Show both age confirmations and the age range in the eligibility section | Grant admin app | in-baseline | A4 — 4.5 | Δ4 Hers, and the most explicit item in either email. Source 2, 2026-09-08, item 7. Age, verbatim: “We will be adding an additional question to the application. For carers, there must also be a box confirming that the person they support is over 18. It would be good to include this in the eligibility section, along with the ‘age range’ as this can help to sense-check it if additional answers don’t seem to correspond.” — then both confirmations listed as bullets. Her reason was never recorded here and is the useful part: the age range sits beside the confirmations so she can spot answers that do not agree | S | Δ4 One phrase was ours, not hers: “rather than under Consent”. She asked to include it in eligibility; that it currently sits in the Consents section is a fact from the form, but move-or-also-show is our reading again (as in EF-33). Here it may matter more: rev_ageconfirmationconsent and its date are consent evidence, and EF-39 keeps the date columns for exactly that reason — so moving the confirmation out of Consent trades evidence grouping for working convenience. Ask; and if it must be one place, her stated purpose puts it in eligibility. Δ4 No longer blocked — EF-35's columns land ahead of Alex, so the carer confirmation just reads empty until the form sends it | Age eligibility is on the tab for eligibility, but the extra column for age confirmation by the carer is not there
Done in the admin app. Not in the trustee portal yet. | EF-37 Δ4 | Show the questions as worded on the form — she cannot tell which is which | Δ Grant admin app + trustee portal | in-baseline | A4 — 4.5 Δ and A6 — 6.8 | Δ Now specified to the field and the order. Labels mirror the web form's wording; "Support recipient condition profile" means a carer completing conditions on behalf of the person they support; the care-support description merges into the same section; the field order is conditions/illnesses → brief disability description → care support details, including hours. Δ4 The packs confirm that exact order | S → M | Δ Now two surfaces, not one. Overlaps EF-17. Δ4 Trap 5 — settled 2026-09-17 as Brief Description of Disability (the packs disagreed; §2f). Two things the check turned up: neither pack carries the form's own wording, so this is our label rather than an application of §1; and the field's subject is constant — the disabled person — with the route changing only who types it (reviewer, 2026-09-17). The carer's own disability and support needs are not recorded at all, which is deliberate and is why EF-35 exists. Δ4 Closed 2026-09-17: both routes land in rev_narrativeraw, and the deployed intake flow already binds it from one trigger key with no route branch — so EF-37 is a form and portal change with no automation work | This is delivered. On the general tab the wellbeing question are shown as the actual questions of the form.
Was already on the applicant table. Now also on application form but the wrong tab. Needs to be moved to general tab. | EF-38 Δ4 | Show whether the applicant is a disabled person, a carer, and so on | Grant admin app | in-baseline | A4 — 4.5 | No new question needed. The form's "Are you" answer is stored as Applicant Type on the Applicant record. Surface it in Support Needs | S | Bundle with EF-01. Δ4 Three values confirmed in live data — A disabled person (38), A carer applying on behalf of a disabled … (14), A carer applying for yourself (11) | on the application form, on the general tab there should be the field applicant type (from the applicant table). This is not delivered.
Done | EF-39 | Remove the date and time stamps on consents | Grant admin app | in-baseline | A4 — 4.5 | Hide them from the form's layout; keep the columns. They add nothing to a caseworker reading the record, and they are the charity's evidence of when each consent was given | S | The one item where the recommendation is not to do exactly what was asked — and the reviewer has agreed with that reading | This is delivered
4.3 New in revision 3 — from the 16 September walkthrough
| Id | What Emily asked for | Surface | Resolution | Reserve | Proposed solution | Size | Depends on / conflicts with
Done | EF-40 Δ5 | County for the grant admin, in a new column | Schema + grant admin app | in-baseline (rework) → change-order-candidate | A4 | The column does not exist — the Applicant entity holds rev_towncity, rev_postcode and rev_locationarea, and no county. Δ5 Settled 2026-09-18 the other way (§2l/1b): a genuinely new column (rev_county or rev_localauthority), not rev_locationarea reuse — populate at intake and use it as the grant admin's location column | M, pending naming | See Trap 4 — this and EF-02 were one decision, no longer are. Check the raw export first: county is column 23 and may be recoverable for historic applications without any lookup. Δ4 Settled 2026-09-17: county goes into the existing rev_locationarea column, for the GRANT ADMIN. Δ5 Reviewer rejected that reuse 2026-09-18 — it would have redefined what the column means (a real option-set change) rather than the disclosure-only rework it was priced as. Back to change-order-candidate (§5b), priced by commercial-agent. Two riders still apply: rev_locationarea is a closed 13-value Choice and county has no clean UK-wide list — ONS returns pseudo-codes for Scotland, Wales and unitary England (§2h-bis), so local authority is the better attribute if funder reporting is the purpose; and the existing option set is shared with rev_anonymisedstatistic regardless of which column county lands on | Rev_localauthority doesn't exist.
Not possible to test yet. Dependency with gravity forms export work from web builder. | EF-41 Δ4 | Postcode → city/county lookup, from Emily's own export | Intake flow + reference data | change-order-candidate | — | The route Emily prefers is Option 1 — load her export as a reference table and look up on the outward code, the same shape as the existing PostcodeRegionMap. Δ4 The file fits that shape exactly: 3,394 rows, one per postcode district, no duplicates, no blanks | M | Δ4 Dependency DELIVERED, and the three questions are answered — see §2h. (1) Provenance: not PAF and not ONSPD — the file has zero alphanumeric outward codes and contains abolished districts, so it is hand-built or scraped. The licence question largely dissolves and becomes a quality question. (2) Province meant Country — four values, England/Scotland/Wales/NI. (3) Staleness still applies and still needs an owner. Two new quality limits: central London will not match at all (no EC1A/WC2H/SW1A — must record a miss, not swallow it), and the county caveat under EF-40. Δ4 Split the pricing: loading this file also repairs region derivation, which is a defect fix against a contracted deliverable, not new capability. Δ4 And the source has changed: ONSPD, not this file (§2h-bis). Queried 2026-09-17, ONSPD_LATEST_UK is a stable endpoint tracking the current quarterly edition, which answers all three questions above outright — provenance is OGL v3, staleness becomes a scheduled job, and the central-London gap does not arise because ONSPD is unit-postcode level. Price the three increments, not the file: (1) a generator seeding the existing outward-code shape, with local authority rendered from the LAD26CD → LAD26NM register and every multi-authority district flagged; (3) the quarterly pull request that makes it sustainable — price these two together; (2) the unit-postcode lookup, a later decision Revitalise can take on the numbers increment 1 produces. One carve-out: Northern Ireland's BT districts need an LPS licence answer from Revitalise first (§5c), and increment 1 leaves them untouched until it arrives | This is not delivered. The change order around postcodes and local authority has been given.
not delivered | EF-42 Δ4 | A Groups bucket in the admin app, grouped by the linkage code | Grant admin app | in-baseline | A4 — 4.5 | Add a Group Applications saved view and Casework sub-area, grouped on rev_grouplinkage — the admin-assigned code the process owner sets by hand | S | The column and its semantics already exist and are already relied on: its own description records that "the combined-amount check groups on this column". Keep it distinct from rev_isgrouptrip, which is the applicant's own claim. Δ4 The codes are free text and inconsistently formed — Round 5 carries 101, RA, 100, 43, 300, with no GP prefix anywhere, so one typo silently splits a group. Δ4 Decided 2026-09-17: it stays manual — a groups table and generated codes are scope creep for this engagement and belong to a later version (§2g). Accepted risk, owned and dated: build the view on the column as it stands and add no validation here, or this item builds the deferred version by instalments. EF-21's Group checkbox is the interim control | There is no special view for group applications that is grouped by the group linkage column under the casework section in the menu
Partly done, but not adjusted based on feedback from the 20th of September | EF-43 Δ4 | A group applications table in the Trustee Portal, above the individual list, with a group detail page | Trustee portal | change-order-candidate | — | A second table above the applications list, one row per group, opening a group detail page. Δ4 The content is now fully specified by the delivered example (§2g): the group row carries group code, member count, group total holiday/activity cost, group total requested, and the shared start/end dates — nothing else. Group total requested is the sum of the members' individual requests — confirmed by the reviewer 2026-09-17, so derive it and store nothing. Δ4 The group's total COST is a different matter and must not be summed: in four of the five groups every member's Total Estimated Cost carries the whole trip's cost, so the sum double-counts — Group RA totals £8,300 against a published £2,075 — while in the fifth the members split it and the sum is correct. Applicants read that field two different ways, so no formula recovers the group cost. Show the requested total, which is safe; either omit the cost from the group row or take it from one authoritative place, and add the field's wording to Alex's list, since the ambiguity is in the question | L | Still the largest genuinely new item. WBS 6.2 specifies a single list screen, so a second entity-level table with its own detail route is a new screen. Δ4 Dependency DELIVERED and the design is now mostly settled. The group pack omits Current Circumstances in 12 of 12 — so the group detail page does not need the score breakdown, which removes the biggest unknown. Only the interaction model (expandable rows vs. separate page) is still open, and it is now a small question rather than an open-ended one. Δ4 One line for the design step: group linkage stays a manual free-text code by decision (§2g), and a mistyped one shows the board a group of four as a group of three. Put the member count on the group row so a split group looks wrong at a glance — presentation, not validation, so it stays inside the accepted scope | There is a group applications table in the trustee portal. It doesn't look good. There is not enough white space bewtween the groups table and the filters under it for the individual applications. Also, it is weird to have a table, a set of filters and then another table. Create a separate screen for group applications, that is a copy of the screen for individual applications. Keeping it separate looks more clean. The group applications screen should have the screen title, the filter bar and the table with group applications. The group applications table should be removed from the application list screen so that screen only has individual applications. When you click on an individual item of a group there is no way to navigate back to the group detail page. Make sure to correct that when building the separate group applicaitons screen. There should be an extra navigation button in the navigation bar for group applications.
Done | EF-44 | Move the scoring-calculation text to an audit-only column, out of the Trustee Portal | Scoring flow + schema | in-baseline | A2 — 2.7 | Split rev_scorebreakdown into two — see §2c. A trustee-facing breakdown (question text and answer label, per EF-07 / EF-24) and a new admin-only audit column recording the threshold values in force at the moment of scoring, the status derived, and the rule that produced it | M | Sequence before EF-07 and EF-24, which otherwise write to a column about to change meaning. Urgent for a reason the walkthrough did not state: four thresholds are seeded PROVISIONAL pending OQ-001/002/003 and Emily is about to settle them (EF-46). Applications scored before that change are only defensible if the audit column exists first | Yes, there is a second compose for the audit text. The questions still have "question 1" generic labels.
Done | EF-45 | An auto-reject reason shown per application | Scoring flow + schema | in-baseline | A2 — 2.7 | Feasible, and cheaper than it sounds. The flagging step already evaluates each rejection condition in order; write the deciding condition to a column as it does. Emily's question was whether it can be automatic — it can, because the flow knows the answer at the moment it sets the status | S | Δ4 Placed 2026-09-17: on the Casework tab, immediately beside rev_status — the reviewer's reason is that the status and why it was reached should read as one thing, so a caseworker opening an application takes both in at a glance. That is adjacency, not just a tab assignment, and it fixes the first section of EF-47's new tab (see its section order). Evaluate with EF-44 and EF-34, not separately: all three write to the scoring flow's output, and EF-34 adds a second rejection path that makes a reason field more valuable. Order matters — if both the threshold and the 12-month rule reject an application, the reason must be deterministic, so fix the evaluation order explicitly rather than inheriting it | Auto reject reason field is there but not populated by the scoring workflow with auto-rejected case. Also, the application doesn't get auto-rejected based on the received funding before questions.
| EF-46 Δ4 | Review and settle the scoring settings — borderline band, income ceiling | Settings | answer-only → decision | A2 — 2.7 (re-seed only) | Not a build item — a decision item, and it closes three open SDD questions. KnockoutThreshold (20), BorderlineBandLower (21), BorderlineBandUpper (30) and IncomeCeiling (£25,000) are all seeded PROVISIONAL pending OQ-001, OQ-002 and OQ-003. Δ4 Emily can now be shown what those values do to two real rounds — Round 4 splits 1 auto-reject / 11 borderline / 51 auto-pass, Round 5 groups 0 / 1 / 11 (§2j). At 20, the knockout threshold filters one application in 63 | S | Sequence this first, because it is free and it gates others. Δ4 Send her §2j's Round 4 / Round 5 distribution with the settings page — the applications she sees in the environment are demo data (§6, DEV and Acceptance hold demo data), so the on-screen effect of a threshold is not evidence for choosing it. Re-seed all three environments together — dev-scoring-settings.json, test-settings.json and prd-settings.json each hold their own copy and are not read from one another at run time. Δ4 Check IncomeCeiling's use in the scoring flow before re-seeding: 90% of Round 4 has no income band at all (§2i), so a ceiling test against a blank value is the majority path, not the exception
4.4 New in revision 4
EF-47 comes from the reviewer, not from Emily. EF-48 and EF-49 come from reading the delivered documents against source — nobody raised either. All three are marked so, because an item's origin changes who confirms it.
| Id | What is asked for | Surface | Resolution | Reserve | Proposed solution | Size | Depends on / conflicts with
Done | EF-47 | A separate tab on the Application form holding every case-work handling field, to remove confusion for Emily | Grant admin app | in-baseline | A4 — 4.5 | Move the casework fields off the General tab onto a new Casework tab — see the inventory below. The General tab currently does four jobs at once, and that is the confusion | M | Raised by the reviewer, 2026-09-17. Not standalone — it is the organising principle six existing items land on. Sequence it first in the A4 pass | This is delivered. There is a Casework tab.
| EF-48 Δ4 | An exceptional-funding reason the trustees never see | Trustee portal (category) · EX-003 (free text) | build (category) + blocked (free text) | A4 — 4.5 (surface the category) · EX-003 (the explanation) | Found in the packs, then confirmed by Emily without either side seeing the other. Exceptional Circumstance is blank in all 63 Round 4 packs, including the 14 carrying an exceptional amount of £99–£3,000. The intake binds both exceptional_circumstance and exceptional_funding_detail, so the reason is recorded and simply does not reach the trustees who decide | S | Disclosure, not capture — corrected by the reviewer 2026-09-17 (§2k). The free-text half is EF-06's answer: rev_exceptionalfundingdetail is IsSecured=1 and its unsecured twin rev_exceptionalfundingdetailredacted waits on narrative scrubbing (WBS 5.2, EX-003) — send the two together. The buildable half is the category: rev_exceptionalcircumstance is deliberately unsecured and trustee-visible, so putting it on the trustee list waits on nothing. Δ4 Emily's own checkbox list names Exceptional Circumstance as one of her eight difficulty areas — she hits the same gap manually today, from the other direction and without sight of this plan. Whether the live form still asks the question is Alex's to confirm, not Emily's; the packs cannot settle it and neither can DEV or Acceptance (§6, DEV and Acceptance hold demo data). EF-21's checkbox is the interim control either way | This is to solve later on when narrative scrubbing is done.
Done | EF-49 | Region is derived wrongly for five postcode areas | Intake flow + settings | in-baseline — defect | A4 — 4.5 | Found by reconciling Emily's postcode file against the seeded PostcodeRegionMap (§2h). BB → West Midlands (should be North West), PE → East Midlands, WD → London, and CT/HP → Not known. 125 of 3,394 districts. BB is wrong rather than absent because the documented "longest prefix wins" rule falls back to B for Birmingham | S | A live defect against a contracted deliverable, not new capability — rev_locationarea feeds the trustee list, the round statistics and the funder reporting EF-03 exists to improve. Fixable today by adding the five prefixes, independently of EF-41. Do not bundle it into EF-41's change order | The settings have not been reseeded. So, I can't verify if this has been built