## Summary
# | Automation | Phase | Platform | Hours (Low) | Hours (High) | Tasks | Annual Hours Saved | Dependencies
0 | Platform Foundation & Governance | Phase 0 | Power Platform + Dataverse + M365 | 37 | 61 | 10 | — | M365 admin access, service account licensing, DPO sign-off
1 | Form Validation & Completeness | Phase 1 | WordPress + spec | 16 | 24 | 6 | 146 | Alex (website designer), WP form plugin confirmation
2 | Scoring Engine | Phase 2 | Power Automate + Dataverse | 22 | 32 | 8 | 6 | Board cutoff decision, scoring methodology sign-off, Automation #4
3 | DocuSign Acceptance Workflow | Phase 1 | Power Automate + DocuSign | 20 | 30 | 7 | 270 | DocuSign licence, acceptance letter template
4 | WordPress → Dataverse Intake | Phase 2 | Power Automate + Dataverse | 14 | 22 | 5 | 49 | Alex (webhook config), Dataverse table design
5 | Narrative Scrubbing (free-text) | Phase 3 | Power Automate + AI Builder | 17 | 26 | 7 | 123 | AI Builder credits (may be bundled), redaction rules, Automation #4, DPO sign-off
6 | Trustee Review Portal | Phase 3 | Dataverse (Power Apps) | 22 | 35 | 8 | 27 | Power Apps premium seats / PAYG, Automation #5, trustee buy-in, DPO sign-off
7 | QuickBooks Duplicate Check | Phase 4 | Power Automate + QBO + Dataverse | 16 | 26 | 5 | 9 | QBO API access, Payment table (#8)
8 | Finance: Provider, Bank Account & Payment | Phase 4 | Dataverse + Power Apps | 13 | 21 | 5 | — | Data model sign-off, finance role (0.5)
| TOTAL |  |  | 177 | 277 | 61 | 630

## WBS Detail
Task ID | Automation # | Automation Name | Task | Description | Hours (Low) | Hours (High) | Depends On | Phase | Deliverable | Status | Actual Hours | Delta
0.1 | 0 | Platform Foundation & Governance | Solution architecture design | Document overall solution approach, environment strategy (dev/prod), naming conventions, component map, integration architecture. Establish solution packaging strategy for ALM | 4 | 6 | — | Phase 0 | Solution architecture document | Done
0.2 | 0 | Platform Foundation & Governance | Power Platform environment setup | Create development and production environments. Configure DLP policies, connector governance, environment security groups. Set up managed solutions | 3 | 5 | 0.1 | Phase 0 | Configured environments | Done
0.3 | 0 | Platform Foundation & Governance | Service account setup | Create service accounts for Power Automate flows. Assign Power Automate premium licences (plus the maker's Power Apps premium). Configure MFA/Conditional Access exceptions. Document credentials securely | 2 | 3 | 0.2 | Phase 0 | Service accounts + credential store | Done
0.4 | 0 | Platform Foundation & Governance | Dataverse solution & table schema build | Create the Power Platform solution and build the seven Dataverse tables (Applicant, Application, Review, Grant, Provider, Bank Account, Payment) plus the Anonymised Statistic snapshot: columns, option sets, autonumber keys (REV-A-00001, GA-2026-00001) and all relationships. Configure the one SharePoint library for signed PDFs and the permission groups. Also includes the Grant Administration model-driven app (rev_grantadministration), the administrative surface for these tables and the Pending/Rejected/Borderline views (task 2.2) — shipped as part of this task but not previously named as its own deliverable (WBS v0.6 correction, EX-002). | 5 | 8 | 0.1 | Phase 0 | Dataverse solution + table schema + Grant Administration app | Done
0.5 | 0 | Platform Foundation & Governance | Security roles & field-level security | Define three Dataverse security roles (admin, finance, trustee) and a field-level (column) security profile on the trustee role that hides identity columns. Review Conditional Access. Gated on DPO (Rebecca Young) sign-off that field-level security may replace the manual, physically-separate control | 4 | 6 | 0.3, 0.4 | Phase 0 | Security roles + field-security profile + DPO sign-off | Done
0.6 | 0 | Platform Foundation & Governance | ALM & deployment strategy | Define dev→prod promotion process. Set up solution export/import procedures. Document versioning approach and rollback procedures. Test deployment pipeline | 3 | 5 | 0.2 | Phase 0 | Chapter in Solution Architecture | Done
0.7 | 0 | Platform Foundation & Governance | Data governance & compliance | Define data retention policies for applicant PII. Establish backup approach. Document GDPR/data protection considerations. Configure data loss prevention policies | 2 | 4 | 0.4, 0.5 | Phase 0 | Data governance framework | Partially done
0.8 | 0 | Platform Foundation & Governance | Governance documentation & handover plan | Write operations runbook: who owns what, licence renewal schedule, monitoring approach, escalation paths, handover checklist for ongoing management | 3 | 5 | 0.5, 0.6, 0.7 | Phase 0 | Governance runbook | Done
0.9 | 0 | Platform Foundation & Governance | Monitoring, logging & alerting foundation | Build the operational Error Log table (no personal data) and the REV ¦ Ops ¦ Failure Alert child flow; establish the reusable error-handling scope pattern that flows call on failure; add a monitoring view over the Error Log plus alerts for AI Builder credit consumption and licence renewal. | 6 | 10 | 0.4 | Phase 0 | Error Log table + Failure Alert flow + monitoring view | Done
0.10 | 0 | Platform Foundation & Governance | Flow error-handling instrumentation | Wrap each cloud flow in the error-handling scope that logs to the Error Log table and calls the Failure Alert flow; executed as each flow is built (about 0.5–1 hour per flow). | 5 | 9 | 0.9 | Phases 1–4 | Instrumented flows | Partially done
1.1 | 1 | Form Validation & Completeness | Audit current form | Document all current fields, identify gaps, map conditional logic requirements. Session with Emily to walk through current pain points | 2 | 3 | — | Phase 1 | Field audit document
1.2 | 1 | Form Validation & Completeness | Write form specification | Field-by-field spec with validation rules, error messages, conditional logic map, progress bar requirements | 4 | 6 | 1.1 | Phase 1 | Form specification brief
1.3 | 1 | Form Validation & Completeness | Design confirmation screen | Layout and copy for the pre-submission summary screen with edit-per-section capability | 1 | 2 | 1.2 | Phase 1 | Confirmation screen spec
1.4 | 1 | Form Validation & Completeness | Review spec with Emily + Alex | Walkthrough of spec with Emily for content accuracy and Alex for technical feasibility. Process feedback and update spec | 3 | 4 | 1.3 | Phase 1 | Reviewed spec
1.5 | 1 | Form Validation & Completeness | Test Alex's implementation | Test built form against spec, verify validation rules and conditional logic, test with sample applicant profiles, log issues | 4 | 6 | 1.4 | Phase 1 | Test report / sign-off
1.6 | 1 | Form Validation & Completeness | Document save-and-continue workflow | Specify how partial submissions are stored and resumed, including data retention period | 2 | 3 | 1.2 | Phase 1 | Save-and-continue spec
2.1 | 2 | Scoring Engine | Design Dataverse table schema (scoring) | Validate the Application table's scoring columns, calculated fields, choice/option sets and views against the v0.2 data model. Session with Emily to confirm field mapping against the current Excel | 3 | 4 | — | Phase 2 | Dataverse table schema (scoring) | Done
2.2 | 2 | Scoring Engine | Configure scoring columns + Settings | Configure the Application scoring columns and the calculated Total Score / Status / Income Flag on the Dataverse table, plus a Settings mechanism (environment variables or a Settings table: knockout threshold, income ceiling). Configure the Pending / Rejected / Borderline views | 2 | 3 | 2.1 | Phase 2 | Configured scoring columns + settings | Done
2.3 | 2 | Scoring Engine | Build scoring flow | Power Automate cloud flow: triggered on a new Dataverse Application row, calculates Q1 inversion + Q2/Q3 Likert mapping, writes total score. Handle missing/null values | 4 | 6 | 2.2 | Phase 2 | Power Automate flow | Done
2.4 | 2 | Scoring Engine | Build knockout/flagging logic | Extend flow: compare score to threshold from Settings, set status (Auto-pass/Borderline/Auto-reject), check income ceiling | 2 | 3 | 2.3 | Phase 2 | Extended flow | Done
2.5 | 2 | Scoring Engine | Build daily summary email | Power Automate scheduled flow: count new applications, auto-rejected, borderline; send summary to Emily | 2 | 3 | 2.3 | Phase 2 | Scheduled summary flow | Done
2.6 | 2 | Scoring Engine | Walkthrough with Emily | Demo the scoring flow with real application examples. Collect feedback on score display, status labels, view layout, summary email format | 3 | 4 | 2.4, 2.5 | Phase 2 | Feedback log
2.7 | 2 | Scoring Engine | Process feedback + rework | Adjust flow, views, and Settings based on Emily's feedback. Re-test changed components | 3 | 4 | 2.6 | Phase 2 | Updated flow
2.8 | 2 | Scoring Engine | Test with real data + sign-off | Run 15-20 real applications through the flow. Verify scores match Emily's manual calculations. Edge case testing (missing answers, boundary scores) | 3 | 5 | 2.7 | Phase 2 | Test results / sign-off
3.1 | 3 | DocuSign Acceptance Workflow | Design DocuSign template | Replicate current Canva acceptance form as a DocuSign template with merge fields and signing positions. Review with Emily for accuracy | 4 | 6 | — | Phase 1 | DocuSign template
3.2 | 3 | DocuSign Acceptance Workflow | Build trigger flow | Power Automate flow: triggered when an application status changes to 'Approved', creates a DocuSign envelope from template with pre-populated fields. Initially triggered manually; connects to the Dataverse Application table once Phase 2 is complete | 4 | 6 | 3.1 | Phase 1 | Power Automate flow
3.3 | 3 | DocuSign Acceptance Workflow | Configure reminders + escalation | Set DocuSign auto-reminders (3 days, 7 days). Build escalation flow: Teams notification to Emily at 14 days unsigned | 2 | 3 | 3.2 | Phase 1 | Reminder configuration
3.4 | 3 | DocuSign Acceptance Workflow | Build completion flow | On both signatures received: update the Grant status to 'Acceptance Signed' in Dataverse and link the signed PDF. Connects to the Dataverse tables once Phase 2 is complete | 3 | 4 | 3.2 | Phase 1 | Completion flow
3.5 | 3 | DocuSign Acceptance Workflow | End-to-end test + feedback | Send test envelopes through full cycle (create, sign, complete). Walkthrough with Emily. Process feedback and adjust | 4 | 6 | 3.4 | Phase 1 | Test results / sign-off
3.6 | 3 | DocuSign Acceptance Workflow | Document fallback process | Write SOP for non-digital applicants: print PDF, post, receive signed copy, scan and attach manually | 2 | 3 | 3.1 | Phase 1 | Fallback SOP
3.7 | 3 | DocuSign Acceptance Workflow | Bulk approval test | Test batch processing: approve 5 applications at once, verify all envelopes created correctly with correct data | 1 | 2 | 3.5 | Phase 1 | Bulk test results
4.1 | 4 | WordPress → Dataverse Intake | Confirm WP plugin capabilities | Work with Alex to identify webhook, email notification, or REST API options in the current form plugin. Document findings | 2 | 4 | — | Phase 2 | Plugin capabilities report | In progress
4.2 | 4 | WordPress → Dataverse Intake | Create field mapping document | Map each WP form field to the corresponding Dataverse column. Define data transformations. Review with Emily | 2 | 3 | 4.1, 2.1 | Phase 2 | Field mapping document | Done
4.3 | 4 | WordPress → Dataverse Intake | Build intake flow | Power Automate flow: HTTP trigger (webhook) or email trigger, parse payload, create a Dataverse Application row with reference number. Handle error cases (malformed data, duplicate submissions) | 4 | 6 | 4.2 | Phase 2 | Power Automate intake flow | Done
4.4 | 4 | WordPress → Dataverse Intake | Build notification + error handling | On successful intake: Teams notification with applicant name and reference number. On failure: alert to Emily with error details | 2 | 3 | 4.3 | Phase 2 | Notification flow | Done
4.5 | 4 | WordPress → Dataverse Intake | End-to-end test + iteration | Submit 10 test applications through WordPress, verify they arrive correctly in Dataverse with scores calculated. Test edge cases (special characters, long text, missing optional fields). Process feedback | 4 | 6 | 4.3, 2.3 | Phase 2 | Test results / sign-off
5.1 | 5 | Narrative Scrubbing (free-text) | Define free-text redaction rules | Session(s) with Emily: which narrative fields (benefit statement, 'other condition' notes) need redaction and which patterns to catch. Structured identifiers are handled by field-level security, not stripped | 3 | 4 | — | Phase 3 | Redaction rules document
5.2 | 5 | Narrative Scrubbing (free-text) | Test AI Builder PII detection | Run 15+ sample narratives through the AI Builder pre-built PII model. Assess detection accuracy, identify gaps, document false positives/negatives | 3 | 4 | 5.1 | Phase 3 | PII detection test results
5.3 | 5 | Narrative Scrubbing (free-text) | Build AI narrative scrubbing | Power Automate flow: on approval, send the free-text narratives to AI Builder PII detection, replace entities with category labels, and write a redacted, pseudonymised copy to the trustee-visible narrative field on the record | 4 | 6 | 5.2, 0.4 | Phase 3 | Narrative scrubbing flow
5.4 | 5 | Narrative Scrubbing (free-text) | Build confidence flagging | If AI confidence < 85%, flag for manual review in a 'Review Required' view; build Emily's review step | 2 | 3 | 5.3 | Phase 3 | Flagging logic
5.5 | 5 | Narrative Scrubbing (free-text) | Walkthrough with Emily + feedback | Demo the redacted narrative output to Emily. Review for missed PII and accuracy. Collect feedback | 1 | 2 | 5.4 | Phase 3 | Feedback log
5.6 | 5 | Narrative Scrubbing (free-text) | Process feedback + rework | Adjust AI thresholds and redaction rules based on Emily's review | 2 | 3 | 5.5 | Phase 3 | Updated flow
5.7 | 5 | Narrative Scrubbing (free-text) | End-to-end test on a board cycle | Run narrative scrubbing on one board cycle's approved applications; Emily reviews the trustee view for missed PII; final threshold calibration | 2 | 4 | 5.6 | Phase 3 | Test results / sign-off
6.1 | 6 | Trustee Review Portal | Design the trustee Dataverse app + security role | Design the canvas/model-driven app screens over the secured Application, Review and Grant tables; confirm the field-level security profile drives what loads | 4 | 6 | 5.3 | Phase 3 | App design + trustee role
6.2 | 6 | Trustee Review Portal | Build applications list screen | App screen: all eligible applications with score, region, dates, status; sortable and filterable; reads live secured data | 3 | 5 | 6.1 | Phase 3 | List screen
6.3 | 6 | Trustee Review Portal | Build application detail screen | Per-application screen: the redacted narrative field, score breakdown, holiday details, staff recommendation | 3 | 5 | 6.1 | Phase 3 | Detail screen
6.4 | 6 | Trustee Review Portal | Build decision capture | Approve / Defer / Reject per application with notes, writing to the Review table. Validate behaviour on multiple devices | 3 | 5 | 6.2 | Phase 3 | Decision capture
6.5 | 6 | Trustee Review Portal | Share app to trustee role + access test | Share the Dataverse app to the trustee security role; test access with trustee accounts; add a print/PDF option | 2 | 3 | 6.2, 6.3 | Phase 3 | Shared app + access test
6.6 | 6 | Trustee Review Portal | Build finalise-decisions flow | Power Automate: Emily clicks 'Finalise', reads decisions from the Review table, updates the Grant records, triggers DocuSign for approved. Handle partial decisions | 3 | 4 | 6.4, 3.2 | Phase 3 | Finalise flow
6.7 | 6 | Trustee Review Portal | Demo to trustees + feedback | Walk Kevin and other trustees through the app. Collect feedback on usability, data presentation, decision workflow | 2 | 3 | 6.5, 6.6 | Phase 3 | Feedback log
6.8 | 6 | Trustee Review Portal | Process feedback + rework | Adjust screens, detail content and the decision form based on trustee feedback. Re-test end-to-end | 2 | 4 | 6.7 | Phase 3 | Updated app / sign-off
7.1 | 7 | QuickBooks Duplicate Check | API feasibility check | Connect the Power Automate QBO connector. Test read access. Confirm searchable fields on grant payment records. Document API limitations | 3 | 5 | — | Phase 4 | Feasibility report
7.2 | 7 | QuickBooks Duplicate Check | Build duplicate-payment lookup flow | Power Automate flow: when a Payment row is created, match against QuickBooks on the holiday provider (from the Grant), holiday dates and grant reference; flag a possible double-pay on the Payment row before issue. Handle fuzzy matching | 6 | 10 | 7.1, 8.1, 4.3 | Phase 4 | Duplicate-payment flow
7.3 | 7 | QuickBooks Duplicate Check | Test with known duplicates | Create test Payment rows matching existing QBO records. Test edge cases: partial matches, changed details. Verify flags appear correctly | 3 | 4 | 7.2 | Phase 4 | Test results
7.4 | 7 | QuickBooks Duplicate Check | Build fallback (if API fails) | Quarterly QBO export cross-referenced against Payment rows via a Power Automate flow. Document the manual process for edge cases | 2 | 4 | 7.1 | Phase 4 | Fallback flow
7.5 | 7 | QuickBooks Duplicate Check | Walkthrough with Emily + feedback | Demo duplicate detection to Emily with real-world examples. Discuss false positive/negative handling. Collect feedback | 2 | 3 | 7.3 | Phase 4 | Feedback log / sign-off
8.1 | 8 | Finance: Provider, Bank Account & Payment | Finalise finance tables | Finalise the Provider, Bank Account and Payment tables, relationships and the single-payee model scaffolded in 0.4; add the finance-specific columns and option sets | 3 | 5 | 0.4 | Phase 4 | Finance tables
8.2 | 8 | Finance: Provider, Bank Account & Payment | Build finance security role | Table/field security so the Bank Account and Payment tables are visible only to the finance role | 2 | 4 | 0.5 | Phase 4 | Finance role
8.3 | 8 | Finance: Provider, Bank Account & Payment | Build payment capture form | Light Power Apps form for the finance role to record providers, bank accounts and payments, with the QuickBooks reference | 4 | 6 | 8.1, 8.2 | Phase 4 | Payment capture form
8.4 | 8 | Finance: Provider, Bank Account & Payment | Wire Payment to Grant + payee logic | Payment names one Payee (a Bank Account) — a provider account or an applicant reimbursement; keep the provider via the Grant for reporting | 2 | 3 | 8.1 | Phase 4 | Payee logic
8.5 | 8 | Finance: Provider, Bank Account & Payment | Test finance flow | Record test payments (provider and reimbursement); verify security and the duplicate-payment hook (#7) | 2 | 3 | 8.3, 8.4 | Phase 4 | Test results

## Phase Timeline
Phase | Duration | Automations | Build Hours (Low) | Build Hours (High) | Key Milestones | Go/No-Go Gate
Phase 0 | Weeks 1–3 | #0 Platform Foundation & Governance | 37 | 61 | Solution architecture documented Dataverse tables + security roles built Service accounts configured Field-level security profile defined Security model approved ALM pipeline tested Governance runbook delivered Monitoring, logging & alerting in place | M365 admin access confirmed Service account licensing agreed DPO signs off field-level security Data governance signed off flow instrumentation (0.10) executed incrementally across Phases 1–4
Phase 1 | Weeks 4–7 | #3 DocuSign Acceptance #1 Form Validation | 36 | 54 | DocuSign template approved End-to-end signature test Bulk approval tested Form validation spec agreed with Alex Feedback cycles complete | DocuSign licence active Fallback SOP approved Alex confirms validation rules Emily signs off on both workflows
Phase 2 | Weeks 8–11 | #4 WP→Dataverse Intake #2 Scoring Engine | 36 | 54 | Dataverse Application table live Intake flow tested with real data Scoring verified with Emily DocuSign flow connected to Dataverse Feedback cycles complete | Emily confirms scoring logic Alex confirms webhook capability End-to-end intake tested
Phase 3 | Weeks 12–15 | #5 Narrative Scrubbing #6 Trustee Review Portal | 39 | 61 | AI free-text redaction validated Field-level security tested Trustee Dataverse app demoed Feedback cycles complete for both | Power Apps premium seats / PAYG agreed Trustees agree to use the app Emily approves scrubbing quality DPO sign-off in place
Phase 4 | When ready | #7 QuickBooks Duplicate Check #8 Finance tables | 29 | 47 | Finance tables + payment capture built Duplicate-payment check tested Emily walked through process | QBO API access granted Payment/Grant fields confirmed Finance role approved False positive handling agreed